## Summary
LIS iOS Implementation Estimate
Greenfield estimate with existing APIs, known Windows/Web behavior and active use of AI development tools
BASELINE HOURS |  | AUTO UPDATE |  | CONTINGENCY |  | BUFFERED TOTAL
300 |  | 35 |  | 15% |  | 345
Schedule Metric | Value |  | Workstream | Hours | % Total
Productive hours / week | 35 |  | Foundation | 18 | 6%
Baseline working weeks | 8.5714 |  | Access & Data | 42 | 14%
Buffered working weeks | 9.8571 |  | Map & Field Workflow | 92 | 30.67%
Buffered calendar months | 2.2765 |  | Reliability & Delivery | 66 | 22%
|  |  | Auto Layers Update | 35 | 11.67%
|  |  | Testing & Release | 47 | 15.67%
Key Scope Notes
• The 300-hour baseline assumes zero iOS implementation credit and includes the automatic monthly map/layer update capability.
• Existing stable APIs, known LIS Desktop/Web behavior and AI development tools are reflected in the estimate.
• A 15% contingency is shown separately; it is not hidden inside the 300 baseline hours.
• Calendar duration depends on device access, review cycles, API stability and field-test availability.

## Detailed Estimate
LIS iOS — Greenfield Implementation Estimate
Baseline target: 300 hours. Estimate assumes the iOS application has not been built yet.
ID | Module | Scope / Included Work | Hours | % Total | Primary Deliverable | Dependency | Risk
1 | Project Setup & Release Foundation | Xcode project, environments, dependency setup, configuration, signing baseline and app structure. | 8 | 2.667% | Buildable project foundation | Apple account / Xcode | Low
2 | Architecture & Core Models | App state, domain models, service/repository boundaries, shared errors and dependency injection. | 10 | 3.333% | Maintainable SwiftUI architecture | Project setup | Low
3 | Authentication & Regio | Keycloak login, Keychain storage, session expiry/refresh, /auth/me, logout and regio resolution. | 16 | 5.333% | Secure authenticated session | Stable auth APIs | Medium
4 | API Client & DTO Mapping | Reusable API client, request/response handling, DTOs, model mappers and authenticated calls. | 14 | 4.667% | Typed API integration layer | Authentication | Medium
5 | Flight Plan Selection & Opening | Fetch regional plans, list/select/open flow, download required data and create active session. | 12 | 4% | Usable plan preparation flow | API client | Low
6 | Offline TPK/TPKX Basemap | Import, validate, store and load offline tile packages; missing/corrupt/storage handling. | 14 | 4.667% | Reliable offline basemap | ArcGIS SDK | Medium
7 | Map Workspace & Geometry Layers | ArcGIS map, points, lines, polygons, symbols, selection, locked layers and map interactions. | 26 | 8.667% | Operational inspection map | Plans + basemap | High
8 | Inspection Workflow | Shared point/geometry form, notes, statuses, item colors, open-item workflow and list/map synchronization. | 20 | 6.667% | Complete local inspection flow | Map workspace | Medium
9 | Local Storage & Recovery | Autosave, active-session JSON, finished plans, atomic writes, restart/crash recovery and safe cleanup. | 24 | 8% | No-loss local-first storage | Core models | High
10 | GPS, Helicopter & Flight Path | CoreLocation permissions, current position, speed/altitude/course, red path and local track storage. | 16 | 5.333% | Live flight navigation data | Map + local storage | Medium
11 | Photos & Attachments | Camera, photo library/files, local originals/thumbnails, point/geometry attachment and safe retention. | 16 | 5.333% | Local-first photo workflow | Inspection + storage | Medium
12 | Timer & Action Logs | Start/pause/resume timer, persisted timer state, essential action logging and logs payload. | 8 | 2.667% | Persisted timer and logs | Local storage | Low
13 | Finish, Upload & Retry | Afronden/Verstuur, finished local plan, ArcGIS photo upload, plan/log uploads, retry and duplicate protection. | 26 | 8.667% | Reliable manual upload pipeline | Auth + storage + photos | High
14 | Settings & Critical Error Handling | Logout, pending uploads, storage/map status, permission errors and safe destructive confirmations. | 8 | 2.667% | Basic support and recovery UI | All core modules | Medium
15 | Automatic TPK/Layers Update | Monthly server job, version manifest, app update check, background download, validation, safe swap and rollback. | 35 | 11.67% | Automated versioned map updates | Hosted packages + connectivity | High
16 | Testing, Field QA & TestFlight | Unit/integration/UI tests, real iPad, offline/crash/auth/upload cases, fixes, archive and TestFlight release. | 47 | 15.67% | Pilot-ready tested build | All modules | High
TOTAL BASELINE ESTIMATE |  |  | 300 | 100% | Target total excludes contingency

## Auto Layers Update
Automatic TPK / Operational Layers Update — 35 Hours
Recommended design: server-side monthly generation and publishing; iOS checks, downloads, validates and swaps safely.
ID | Work Item | Included Work | Hours | % Auto Update | Output
1 | Update Architecture | Package/layer ownership, region strategy, version rules and update lifecycle. | 5 | 14.29% | Approved update design
2 | Monthly Generation Job | Scheduled server script/job that generates or publishes the new package/layer release. | 7 | 20% | Repeatable monthly job
3 | Manifest & Integrity Metadata | Version, publish date, URL, size, SHA-256, minimum app version and region metadata. | 4 | 11.43% | Version manifest endpoint/file
4 | iOS Version Check | Check on launch/network return/manual refresh; compare installed and available versions. | 5 | 14.29% | Update availability manager
5 | Background Download & Storage | Background URLSession, progress, space checks, temporary file and resumable behavior. | 5 | 14.29% | Reliable package download
6 | Validation, Atomic Swap & Rollback | Verify integrity and ArcGIS load, avoid active-flight replacement, preserve last-known-good version. | 5 | 14.29% | Safe activation and rollback
7 | Update QA & Failure Scenarios | Interrupted download, invalid manifest/package, low storage, offline mode and monthly rerun testing. | 4 | 11.43% | Verified failure-safe update flow
AUTO UPDATE TOTAL |  |  | 35 | 100% | Included in 300-hour baseline

## Assumptions
Estimate Assumptions & Boundaries
Planning Input |  |  | Value
Productive hours / week |  |  | 35
Contingency |  |  | 15%
Weeks / month |  |  | 4.33
Baseline scope starts from |  |  | Greenfield / zero implementation
# | Assumption | Included Interpretation | Impact if False
1 | Existing APIs are available and stable | No major backend redesign; endpoint contracts can be consumed from Swift. | Add backend analysis/change hours.
2 | Windows/Web workflows are the functional reference | Business rules and expected behavior are known; limited discovery is needed. | Add product discovery and specification time.
3 | AI coding tools are used actively | AI accelerates models, DTOs, SwiftUI scaffolding, refactors and test generation. | Increase implementation hours by approximately 20–35%.
4 | One experienced Swift developer | Estimate is effort, not a fixed calendar promise; parallel staffing is not assumed. | Ramp-up or coordination changes duration.
5 | Auto update uses a server-side monthly schedule | iOS checks/downloads when allowed; iOS does not guarantee exact monthly background execution. | A different update architecture may add scope.
6 | TPK/TPKX package hosting is available | A protected file location or simple endpoint can serve versioned packages and manifest. | Add infrastructure/security implementation.
7 | No advanced Phase-2 extras | No background GPS, external GNSS, advanced admin console or complex conflict resolution. | Estimate separately if requested.
8 | Real-device access is available | A Mac, test iPad and TestFlight access are available throughout development. | External waiting time extends calendar duration.
Reference |  | URL
Apple background downloads |  | https://developer.apple.com/documentation/foundation/downloading-files-in-the-background
Apple background processing |  | https://developer.apple.com/documentation/backgroundtasks/bgprocessingtask
ArcGIS scheduled offline updates |  | https://developers.arcgis.com/swift/v200/sample-code/apply-scheduled-updates-to-preplanned-map-area/