## Summary
LIS iOS Implementation Estimate
300-hour core iOS app + separate 35-hour automatic TPK/layers update module
CORE IOS APP |  | AUTO UPDATE |  | COMBINED BASELINE |  | BUFFERED TOTAL
300 |  | 35 |  | 335 |  | 385.25
Schedule Metric | Value |  | Workstream | Hours | % Total
Productive hours / week | 35 |  | Foundation | 18 | 5.373%
Core app working weeks | 8.5714 |  | Access & Data | 48 | 14.33%
Combined baseline weeks | 9.5714 |  | Map & Field Workflow | 105 | 31.34%
Buffered working weeks | 11.0071 |  | Reliability & Delivery | 78 | 23.28%
Buffered calendar months | 2.5421 |  | Auto Layers Update | 35 | 10.45%
|  |  | Testing & Release | 51 | 15.22%
Key Scope Notes
• The core iOS application is estimated at 300 hours; automatic monthly map/layer updates add 35 hours separately.
• Existing stable APIs, known LIS Desktop/Web behavior and AI development tools are reflected in the estimate.
• The combined baseline is 335 hours; the 15% contingency is shown separately and produces the buffered total.
• Calendar duration depends on device access, review cycles, API stability and field-test availability.

## Detailed Estimate
LIS iOS — Greenfield Implementation Estimate
Core iOS application target: 300 hours. Automatic map/layer updates are estimated separately.
ID | Module | Scope / Included Work | Hours | % Total | Primary Deliverable | Dependency | Risk
1 | Project Setup & Release Foundation | Xcode project, environments, dependency setup, configuration, signing baseline and app structure. | 8 | 2.667% | Buildable project foundation | Apple account / Xcode | Low
2 | Architecture & Core Models | App state, domain models, service/repository boundaries, shared errors and dependency injection. | 10 | 3.333% | Maintainable SwiftUI architecture | Project setup | Low
3 | Authentication & Regio | Keycloak login, Keychain storage, session expiry/refresh, /auth/me, logout and regio resolution. | 18 | 6% | Secure authenticated session | Stable auth APIs | Medium
4 | API Client & DTO Mapping | Reusable API client, request/response handling, DTOs, model mappers and authenticated calls. | 16 | 5.333% | Typed API integration layer | Authentication | Medium
5 | Flight Plan Selection & Opening | Fetch regional plans, list/select/open flow, download required data and create active session. | 14 | 4.667% | Usable plan preparation flow | API client | Low
6 | Offline TPK/TPKX Basemap | Import, validate, store and load offline tile packages; missing/corrupt/storage handling. | 16 | 5.333% | Reliable offline basemap | ArcGIS SDK | Medium
7 | Map Workspace & Geometry Layers | ArcGIS map, points, lines, polygons, symbols, selection, locked layers and map interactions. | 30 | 10% | Operational inspection map | Plans + basemap | High
8 | Inspection Workflow | Shared point/geometry form, notes, statuses, item colors, open-item workflow and list/map synchronization. | 23 | 7.667% | Complete local inspection flow | Map workspace | Medium
9 | Local Storage & Recovery | Autosave, active-session JSON, finished plans, atomic writes, restart/crash recovery and safe cleanup. | 28 | 9.333% | No-loss local-first storage | Core models | High
10 | GPS, Helicopter & Flight Path | CoreLocation permissions, current position, speed/altitude/course, red path and local track storage. | 18 | 6% | Live flight navigation data | Map + local storage | Medium
11 | Photos & Attachments | Camera, photo library/files, local originals/thumbnails, point/geometry attachment and safe retention. | 18 | 6% | Local-first photo workflow | Inspection + storage | Medium
12 | Timer & Action Logs | Start/pause/resume timer, persisted timer state, essential action logging and logs payload. | 10 | 3.333% | Persisted timer and logs | Local storage | Low
13 | Finish, Upload & Retry | Afronden/Verstuur, finished local plan, ArcGIS photo upload, plan/log uploads, retry and duplicate protection. | 30 | 10% | Reliable manual upload pipeline | Auth + storage + photos | High
14 | Settings & Critical Error Handling | Logout, pending uploads, storage/map status, permission errors and safe destructive confirmations. | 10 | 3.333% | Basic support and recovery UI | All core modules | Medium
15 | Testing, Field QA & TestFlight | Unit/integration/UI tests, real iPad, offline/crash/auth/upload cases, fixes, archive and TestFlight release. | 51 | 17% | Pilot-ready tested build | All modules | High
CORE IOS APP TOTAL |  |  | 300 | 100% | Automatic layers update excluded

## Auto Layers Update
Automatic TPK / Operational Layers Update — Separate 35-Hour Add-On
This 35-hour module is separate from the 300-hour core iOS application estimate.
ID | Work Item | Included Work | Hours | % Auto Update | Output
1 | Update Architecture | Package/layer ownership, region strategy, version rules and update lifecycle. | 5 | 14.29% | Approved update design
2 | Monthly Generation Job | Scheduled server script/job that generates or publishes the new package/layer release. | 7 | 20% | Repeatable monthly job
3 | Manifest & Integrity Metadata | Version, publish date, URL, size, SHA-256, minimum app version and region metadata. | 4 | 11.43% | Version manifest endpoint/file
4 | iOS Version Check | Check on launch/network return/manual refresh; compare installed and available versions. | 5 | 14.29% | Update availability manager
5 | Background Download & Storage | Background URLSession, progress, space checks, temporary file and resumable behavior. | 5 | 14.29% | Reliable package download
6 | Validation, Atomic Swap & Rollback | Verify integrity and ArcGIS load, avoid active-flight replacement, preserve last-known-good version. | 5 | 14.29% | Safe activation and rollback
7 | Update QA & Failure Scenarios | Interrupted download, invalid manifest/package, low storage, offline mode and monthly rerun testing. | 4 | 11.43% | Verified failure-safe update flow
AUTO UPDATE TOTAL |  |  | 35 | 100% | Excluded from 300-hour core app

## Assumptions
Estimate Assumptions & Boundaries
Planning Input |  |  | Value
Productive hours / week |  |  | 35
Contingency |  |  | 15%
Weeks / month |  |  | 4.33
Baseline scope starts from |  |  | Greenfield / zero implementation
# | Assumption | Included Interpretation | Impact if False
1 | Existing APIs are available and stable | No major backend redesign; endpoint contracts can be consumed from Swift. | Add backend analysis/change hours.
2 | Windows/Web workflows are the functional reference | Business rules and expected behavior are known; limited discovery is needed. | Add product discovery and specification time.
3 | AI coding tools are used actively | AI accelerates models, DTOs, SwiftUI scaffolding, refactors and test generation. | Increase implementation hours by approximately 20–35%.
4 | One experienced Swift developer | Estimate is effort, not a fixed calendar promise; parallel staffing is not assumed. | Ramp-up or coordination changes duration.
5 | Auto update uses a server-side monthly schedule | iOS checks/downloads when allowed; iOS does not guarantee exact monthly background execution. | A different update architecture may add scope.
6 | TPK/TPKX package hosting is available | A protected file location or simple endpoint can serve versioned packages and manifest. | Add infrastructure/security implementation.
7 | No advanced Phase-2 extras | No background GPS, external GNSS, advanced admin console or complex conflict resolution. | Estimate separately if requested.
8 | Real-device access is available | A Mac, test iPad and TestFlight access are available throughout development. | External waiting time extends calendar duration.
Reference |  | URL
Apple background downloads |  | https://developer.apple.com/documentation/foundation/downloading-files-in-the-background
Apple background processing |  | https://developer.apple.com/documentation/backgroundtasks/bgprocessingtask
ArcGIS scheduled offline updates |  | https://developers.arcgis.com/swift/v200/sample-code/apply-scheduled-updates-to-preplanned-map-area/

## Final Decision iOS
LIS iOS Implementation Estimate
65-hour core iOS app + separate 15-hour automatic TPK/layers update module
CORE IOS APP |  | AUTO Layers UPDATE | COMBINED BASELINE | BUFFERED TOTAL
50 |  | 15 | 65 | 74.75
Workstream | Hours | % Total
Foundation | 8 | 12.31%
Access & Data | 12 | 18.46%
Map & Field Workflow | 14 | 21.54%
Reliability & Delivery | 7 | 10.77%
Auto Layers Update | 15 | 23.08%
Testing & Release | 9 | 13.85%

## Windows Layers auto updates
Auto Layers Update – Windows
5 hours for online layers + 5 layers for offline layers
Online Layers | Offline Layers | COMBINED BASELINE | BUFFERED TOTAL
5 | 5 | 10 | 11.5